## Sprint 1(Spring)
Optical Communication Backlog
Sprint
Stories | Not Started | In Progress | Finished | % Com
Create preliminary design for pointing system. |  |  |  | 0%
Design the power system, including batteries and voltage converters as needed. |  |  |  | 20%
Design, or adjust existing design, the optical system using Keysight PDS. |  |  |  | 0%
Implement pointing system for TX. |  |  |  | 0%
Write codes for containing sensor data, process, and generate the OOK signal. |  |  |  | 90%
Write codes for demodulating the OOK signal on the TX side. |  |  |  | 50%
Integrate and test the TX and RX sub-systems. |  |  |  | 20%
Design a packaging solution for the entire system, using additive manufacturing. |  |  |  | 0%
Integrate all sub-systems and test complete system. |  |  |  | 0%
Use existing lenses to increase range of TX/RX system. |  |  |  | 50%
s