## Sprint 1
Optical Communication Backlog
Sprint 1
Stories | Not Started | Assigned | In progress | % Com | Done
Understand all the materials, designs, devices, from Zhou Banga’s paper and the senior design team from last year. |  | Yes | Yes | 80
Get access to Micaplex 224 (sign lab policies form, get access from Dr. Rojas). |  |  |  |  | Yes
Review literature on low-cost optical systems and confirm performance metrics. |  | Yes | yes | 80
Review sensors of interest (optical camera) |  |  |  |  | Yes
Check existing pointing mechanism, and how to operate it. |  | Yes | yes | 80
Describe in detail the overall system architecture down to voltage and current levels, Digital I/O, Analog I/O, battery voltages, computer and Sensor interface. |  | Yes | Yes | 40
Review laser driver and detector configuration, perform basic performance tests. |  | Yes | Yes | 100 | yes
Identify and order items required for the overall system architecture. Check existing items. |  | Yes | Yes | 50
Design the power system, including batteries and voltage converters as needed. |  | Yes | Yes | 25
Design, or adjust existing design, the optical system using Keysight PDS. |  | Yes | Yes | 100 | yes
Implement pointing system for TX. | Yes | Yes
Write codes for containing sensor data, process, and generate the OOK signal. | Yes | Yes
Write codes for demodulating the OOK signal on the TX side. | YEs | Yes
Integrate and test the TX and RX sub-systems. | Yes | Yes
Design a packaging solution for the entire system, using additive manufacturing. | Yes | No
Integrate and test the entire subsystem. | yes
Complete SDS v1 |  | yes | yes | 100 | yes
Complete SRS v1 |  | yes | yes | 100 | yes