## Sprint 1(Spring)
Optical Communication Backlog
Sprint 1
Stories | Not Started | In Progress | Finished | % Com | Assigned to
Create preliminary design for pointing system. |  |  |  | 0% | Dylan K, Dominic S.
Design the power system, including batteries and voltage converters as needed. |  |  |  | 20% | Matthew S., Cameron M.
Implement pointing system for TX. |  |  |  | 0% | Dylan K, Dominic S.
Write codes for containing sensor data, process, and generate the OOK signal. |  |  |  | 90% | Sean H.
Write codes for demodulating the OOK signal on the TX side. |  |  |  | 50% | Sean H.
Integrate and test the TX and RX sub-systems. |  |  |  | 20% | Cameron M., Sean H., Jarrod S.
Design a packaging solution for the entire system, using additive manufacturing. |  |  |  | 0% | Jarrod S.
Integrate all sub-systems and test complete system. |  |  |  | 0% | Everyone
Use existing lenses to increase range of TX/RX system. |  |  |  | 50% | Matthew S.
s

## Sprint 2 (Spring)
Optical Communication Backlog
Sprint 2
Stories | Not Started | In Progress | Finished | % Com | Assigned to
Create preliminary design for pointing system. |  |  |  | 10% | Dylan K, Dominic S.
Design the power system, including batteries and voltage converters as needed. |  |  |  | 95% | Matthew S., Cameron M.
Construct power distribution and signal modification circuits. |  |  |  | 10% | Dylan K., Matthew S.
Implement pointing system for TX. |  |  |  | 0% | Dylan K, Dominic S.
Write codes for containing sensor data, process, and generate the OOK signal. |  |  |  | 100% | Sean H.
Write codes for demodulating the OOK signal on the TX side. |  |  |  | 60% | Sean H.
Integrate and test the TX and RX sub-systems. |  |  |  | 30% | Cameron M., Sean H., Jarrod S.
Design a packaging solution for the entire system, using additive manufacturing. |  |  |  | 25% | Jarrod S.
Integrate all sub-systems and test complete system. |  |  |  | 0% | Everyone
Use existing lenses to increase range of TX/RX system. |  |  |  | 50% | Matthew S.

## Sprint 3 (Spring)
Optical Communication Backlog
Sprint 2
Stories | Not Started | In Progress | Finished | % Com | Assigned to
Create preliminary design for pointing system. |  |  |  | 10% | Dylan K, Dominic S.
Design the power system, including batteries and voltage converters as needed. |  |  |  | 100% | Matthew S., Cameron M.
Construct power distribution and signal modification circuits. |  |  |  | 50% | Dylan K., Matthew S., Jarrod S.
Implement pointing system for TX. |  |  |  | 0% | Dylan K, Dominic S.
Write codes for containing sensor data, process, and generate the OOK signal. |  |  |  | 100% | Sean H.
Write codes for demodulating the OOK signal on the TX side. |  |  |  | 100% | Sean H.
Integrate and test the TX and RX sub-systems. |  |  |  | 70% | Cameron M., Sean H., Jarrod S.
Design a packaging solution for the entire system, using additive manufacturing. |  |  |  | 35% | Jarrod S. , Matthew S.
Integrate all sub-systems and test complete system. |  |  |  | 50% | Everyone
Use existing lenses to increase range of TX/RX system. |  |  |  | 50% | Matthew S. , Dominic S.