## Sprint 1
Optical Communication Backlog
Sprint 1
Stories | Not Started | In Progress | Finished | % Com
Understand all the materials, designs, devices, from Zhou Banga’s paper and the senior design team from last year. |  |  |  | 100%
Get access to Micaplex 224 (sign lab policies form, get access from Dr. Rojas). |  |  |  | 50%
Review literature on low-cost optical systems and confirm performance metrics. |  |  |  | 100%
Review sensors of interest (optical camera) |  |  |  | 100%
Check existing pointing mechanism, and how to operate it. |  |  |  | 0%
Describe in detail the overall system architecture down to voltage and current levels, Digital I/O, Analog I/O, battery voltages, computer and Sensor interface. |  |  |  | 50%
Review laser driver and detector configuration, perform basic performance tests. |  |  |  | 100%
Identify and order items required for the overall system architecture. Check existing items. |  |  |  | 50%
Design the power system, including batteries and voltage converters as needed. |  |  |  | 25%
Design, or adjust existing design, the optical system using Keysight PDS. |  |  |  | 0%
Implement pointing system for TX. |  |  |  | 0%
Write codes for containing sensor data, process, and generate the OOK signal. |  |  |  | 0%
Write codes for demodulating the OOK signal on the TX side. |  |  |  | 0%
Integrate and test the TX and RX sub-systems. |  |  |  | 0%
Design a packaging solution for the entire system, using additive manufacturing. |  |  |  | 0%
Integrate and test the entire subsystem. |  |  |  | 0%

## Sprint 2
Optical Communication Backlog
Sprint 2
Stories | Not Started | In Progress | Finished | % Com
Get access to Micaplex 224 (sign lab policies form, get access from Dr. Rojas). |  |  |  | 100%
Check existing pointing mechanism, and how to operate it. |  |  |  | 0%
Describe in detail the overall system architecture down to voltage and current levels, Digital I/O, Analog I/O, battery voltages, computer and Sensor interface. |  |  |  | 100%
Identify and order items required for the overall system architecture. Check existing items. |  |  |  | 100%
Design the power system, including batteries and voltage converters as needed. |  |  |  | 50%
Design, or adjust existing design, the optical system using Keysight PDS. |  |  |  | 0%
Implement pointing system for TX. |  |  |  | 0%
Write codes for containing sensor data, process, and generate the OOK signal. |  |  |  | 60%
Write codes for demodulating the OOK signal on the TX side. |  |  |  | 30%
Integrate and test the TX and RX sub-systems. |  |  |  | 10%
Design a packaging solution for the entire system, using additive manufacturing. |  |  |  | 0%
Integrate and test the entire subsystem. |  |  |  | 0%

## Sprint 3
Optical Communication Backlog
Sprint 3
Stories | Not Started | In Progress | Finished | % Com
Check existing pointing mechanism, and how to operate it. |  |  |  | 0%
Design the power system, including batteries and voltage converters as needed. |  |  |  | 50%
Design, or adjust existing design, the optical system using Keysight PDS. |  |  |  | 0%
Implement pointing system for TX. |  |  |  | 0%
Write codes for containing sensor data, process, and generate the OOK signal. |  |  |  | 100%
Write codes for demodulating the OOK signal on the TX side. |  |  |  | 100%
Integrate and test the TX and RX sub-systems. |  |  |  | 20%
Design a packaging solution for the entire system, using additive manufacturing. |  |  |  | 0%
Integrate and test the entire subsystem. |  |  |  | 0%